<Nome do Projeto>

Plano de Desenvolvimento de Software

[Observação: O texto em azul exibido entre colchetes e em itálico (style=InfoBlue) foi incluído para orientar o autor e deve ser excluído antes da publicação do documento. Qualquer parágrafo inserido após esse estilo será definido automaticamente como normal (estilo=BodyText).]

Histórico da Revisão

| Data | Versão | Descrição | Autor |
| --- | --- | --- | --- |
| dd/mm/aaaa | 1.0 | <breve descrição da revisão> | <autores da revisão> |
| dd/mm/aaaa | 1.1 | <breve descrição da revisão> | <autores da revisão> |

### Introduction

#### Purpose

The purpose of this Software Development Plan is to define the development activities in terms of the phases and iterations required for implementing a Collegiate Sports Paging Service for WebNewsOnLine.

#### Scope

This Software Development Plan describes the overall plan to be used by the team for developing the system for . The details of the individual iterations will be described in the Iteration Plans.

#### Definitions, Acronyms and Abbreviations

None.

#### References

- Documento de visão

### Management Process

#### Project Estimates

The Inception phase of this project will take 3 weeks. Initial estimates of subsequent phases can be seen in section 2.4 above.

#### Phase Plan

The development of the will be conducted using a phased approach where multiple iterations occur within a phase. The phases and the relative timeline is shown in the table below:

| Phase | No. of Iterations | Start | End |
| --- | --- | --- | --- |
| Inception Phase | 1 | Week 1 | Week 4 |
| Elaboration Phase | 1 | Week 5 | Week11 |
| Construction Phase | 3 | Week 12 | Week 27 |
| Transition Phase | 1 | Week 28 | Week 31 |

The milestones that mark the end of each phase can be seen in the table below.

| Description | Milestone |
| --- | --- |
| Inception Phase | The Inception Phase will develop the product requirements and establish the business case for the . The major use cases will be developed as well as the high level Project Plan. At the end of the Inception Phase will decide whether to fund and proceed with the project based upon the business case. Business Case Review Milestone at the end of the phase marks the Go/No Go decision for the project. |
| Elaboration Phase | The Elaboration Phase will analyze the requirements and will develop the architectural prototype. At the completion of the Elaboration Phase all use cases selected for Release 1.0 will have completed analysis and design. In addition, the high risk use cases for Release 2.0 will have been analyzed and designed. The architectural prototype will test the feasibility and performance of the architecture that is required for Release 1.0. The Architectural Prototype Milestone marks the end of the Elaboration Phase. This prototype signifies verification of the major architectural components that comprise the R1.0 Release. |
| Construction Phase | During the Construction Phase, remaining use cases will be analyzed and designed. The Beta version for Release 1.0 will be developed and distributed for evaluation. The implementation and test activities to support the R1.0 and R2.0 releases will be completed. The R2.0 Operational Capability Milestone marks the end of the Construction Phase. Release 2.0 software is ready for packaging. |
| Transition Phase | The Transition Phase will prepare the R1.0 and R2.0 releases for distribution. It provides the required support to ensure a smooth installation including user training. The R2.0 Release Milestone marks the end of the Transition Phase. At this point all capabilities, as defined in the Vision Document, are installed and available for the users. |

#### Plano da fase de concepção

The Inception phase of the project can be viewed as follows:

| Task | Start | End |
| --- | --- | --- |
| INCEPTION | Fri 10/1/99 | Mon 10/25/99 |
| Begin Inception | Fri 10/1/99 | Fri 10/1/99 |
| Inception Kick-off | Mon 10/4/99 | Wed 10/6/99 |
| Add tasks to project plan for specific project technology using ContextWISE cartridges | Mon 10/4/99 | Mon 10/4/99 |
| Assemble Change Control Board | Mon 10/4/99 | Tue 10/5/99 |
| Create and baseline Change Control Plan | Tue 10/5/99 | Tue 10/5/99 |
| Obtain Sign-off | Tue 10/5/99 | Tue 10/5/99 |
| Inception Kick-off Meeting | Tue 10/5/99 | Wed 10/6/99 |
| Prepare for inception kick-off meeting | Tue 10/5/99 | Wed 10/6/99 |
| Hold Inception Kick-off Meeting | Wed 10/6/99 | Wed 10/6/99 |
| Inception Kick-off Completed | Wed 10/6/99 | Wed 10/6/99 |
| Inception Deliverables | Wed 10/6/99 | Thu 10/14/99 |
| Hold Requirements Workshop | Wed 10/6/99 | Thu 10/7/99 |
| Project Vision created, reviewed, and signed off | Wed 10/6/99 | Thu 10/7/99 |
| Preliminary Use Case Model (10-20% complete) created and placed under revision control | Thu 10/7/99 | Mon 10/11/99 |
| Preliminary Use Case Survey created, reviewed, and signed off | Mon 10/11/99 | Tue 10/12/99 |
| Preliminary Supplementary Specifications created, reviewed, and signed off | Tue 10/12/99 | Tue 10/12/99 |
| Business Case created, reviewed, and signed off | Tue 10/12/99 | Tue 10/12/99 |
| Preliminary Project Glossary created, reviewed, and signed off | Tue 10/12/99 | Tue 10/12/99 |
| Preliminary Creative Design Brief created, reviewed, and signed off | Wed 10/6/99 | Thu 10/7/99 |
| Preliminary Site Map & Use-Case Navigation Mapping created, reviewed, and signed off | Thu 10/7/99 | Fri 10/8/99 |
| Creative Design Comps created, reviewed, and signed off | Fri 10/8/99 | Mon 10/11/99 |
| Preliminary Content Plan created, reviewed, and signed off (if applicable) | Wed 10/6/99 | Wed 10/6/99 |
| User Interface Prototype (optional) created, reviewed, and signed off | Wed 10/6/99 | Wed 10/6/99 |
| Reports Prototype (optional) created, reviewed, and signed off | Tue 10/12/99 | Thu 10/14/99 |
| Develop Preliminary Technology Alternatives | Wed 10/6/99 | Thu 10/7/99 |
| Establish contact with appropriate Context Gurus | Tue 10/12/99 | Wed 10/13/99 |
| Preliminary Knowledge Transfer Plan & Schedule created, reviewed, and signed off | Wed 10/13/99 | Wed 10/13/99 |
| Validate/Invalidate Assumption from Inception proposal | Wed 10/13/99 | Thu 10/14/99 |
| Obtain Sign-off | Thu 10/14/99 | Thu 10/14/99 |
| Inception Deliverables Complete | Thu 10/14/99 | Thu 10/14/99 |
| Inception Wrap-up | Thu 10/14/99 | Mon 10/25/99 |
| Conduct Quality Check Meeting with Client | Thu 10/14/99 | Thu 10/14/99 |
| Conduct Quality Assurance | Thu 10/14/99 | Fri 10/15/99 |
| Hold Context Lessons Learned Meeting | Thu 10/14/99 | Thu 10/14/99 |
| First project estimates created, reviewed, and signed off (+75%, -60%) | Thu 10/14/99 | Mon 10/18/99 |
| Full Project Iterative Delivery Plan created, reviewed, and signed off | Mon 10/18/99 | Tue 10/19/99 |
| Create proposal for Elaboration Phase | Thu 10/14/99 | Fri 10/15/99 |
| Create Software Project Log | Fri 10/15/99 | Fri 10/15/99 |
| Prepare for Inception Checkpoint | Fri 10/15/99 | Mon 10/18/99 |
| Have team, including client project manager, complete the work release sign-off form | Mon 10/18/99 | Tue 10/19/99 |
| Deliver proposal for Elaboration Phase | Tue 10/19/99 | Thu 10/21/99 |
| Inception Checkpoint Review and Go/No Go Decision | Thu 10/21/99 | Fri 10/22/99 |
| Move appropriate deliverables from Project Homepage to IAN Artifacts | Fri 10/22/99 | Mon 10/25/99 |
| Inception Complete | Mon 10/25/99 | Mon 10/25/99 |

#### Iteration Objectives

| Phase | Iteration | Description | Associated Milestones | Risks Addressed |
| --- | --- | --- | --- | --- |
| Inception | Preliminary Iteration | Defines business model, product requirements, project plan, and business case. | Business Case Review | Clarifies user requirements up front. Develops realistic project plans and scope. Determines feasibility of project from a business point of view |
| Elaboration Phase | Develop Architectural Prototype | Completes analysis & design for all use cases. Develops the architectural prototype. | Architectural Prototype | Architectural issues clarified. Technical risks mitigated. Early prototype for user review. |
| Construction Phase | C1 Iteration – Develop Beta | Implement and test use cases to provide the Beta Version. | Beta | All key features from a user and architectural prospective implemented in the Beta. User feedback prior to release of software. |
|  | C2 Iteration – Develop initial Release | Implement and test remaining use cases, fix defects from Beta, and incorporate feedback from Beta. Develops the initial system. | Software | Software fully reviewed by user community. Product quality should be high. Defects minimized. Cost of quality reduced. |
|  | C3 Iteration – Develop full Release | Incorporate enhancements and defects from initial release. Develops the full system. | Software | Quick release addresses customer satisfaction. All key functionality provided in System by full Release. |
| Transition phase | Software Release | Package, distribute, and install Release. | Software Released |  |